## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16277 | New | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 1043/MURD/12 | 18/04/2023 | 18/04/2023 | Resource Division | 13.2 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16277 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SALU ground water based water supply scheme under Block_ Bharatpur-IIDist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000117/2023-2024 | 1906/MEDB | 16/06/2023 | 16/09/2023 | S. K. ENTERPRISE | 23.82 | 19.53 | 82 | 15
3 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16277 | New | NEW CONNECTION AT SALU PH-I |  |  | BILL/00234/2024-2025 |  | 02/05/2024 | 02/05/2024 | WBSEDCL | 4.09 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16277 | New | NEW CONNECTION AT SALU PH-I |  |  | BILL/00237/2024-2025 | 67/WBSEDCL-JJM | 09/05/2024 | 09/05/2024 | WBSEDCL | 4.09 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16277 | New | SALU & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- BHARATPUR-II of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000279/2023-2024 | 2642/MURD | 23/08/2023 | 29/03/2025 | M/S. CHAKRABORTY & COMPANY | 601.12 | 257.39 | 42.82 | 20
6 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16277 | New | NEW CONNECTION AT SALU PH-II |  |  | BILL/01219/2024-2025 | 302/WBSEDCL-JJM | 06/12/2024 | 06/12/2024 | WBSEDCL | 3.37 | 0 | 0 | 0
7 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16277 | New | NEW CONNECTION AT SALU PH-III |  |  | BILL/01220/2024-2025 | 303/WBSEDCL-JJM | 06/12/2024 | 06/12/2024 | WBSEDCL | 7.77 | 0 | 0 | 0
Total | [13 empty] | 657.46 | 276.92 | 42.12