## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | RAMNA BARAKHARI AND ADJOIMING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16278 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 1043/MURD/7 | 19/04/2023 | 19/04/2023 | Resource Division | 25.05 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | RAMNA BARAKHARI AND ADJOIMING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16278 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under RAMNA BARAKHARI ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000116/2023-2024 | 1905/MEDB | 16/06/2023 | 16/09/2023 | DAS CONSTRUCTION | 22.81 | 16.07 | 70.46 | 8
3 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | RAMNA BARAKHARI AND ADJOIMING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16278 | New | NEW CONNECTION AT RAMNABORKHARI PH-I |  |  | BILL/00236/2024-2025 | 66/WBSEDCL-JJM | 09/05/2024 | 09/05/2024 | WBSEDCL | 3.64 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | RAMNA BARAKHARI AND ADJOIMING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16278 | New | Formal work order for RAMNA BARAKHARI & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission, Block- BHARATPUR-II of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000836/2022-2023 | 833/MURD | 23/03/2023 | 30/09/2025 | PRIYANKA CONSTRUCTION | 483.93 | 183.18 | 37.85 | 7
Total | [13 empty] | 535.44 | 199.26 | 37.21