## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16280 | New | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 1075/MURD/16 | 19/04/2023 |  | Resource Division | 1.09 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Berhampore Mechanical | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16280 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under BHAGULIA ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000264/2023-2024 | 3700/MEDB | 03/11/2023 | 01/02/2024 | A.G. ENTERPRISE | 20.9 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Murshidabad Division | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16280 | New | Material Requisition To Resource Division |  |  | RTOR000338/2023-2024 | 79/MURD/05 | 09/01/2024 |  | Resource Division | 3.82 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16280 | New | NEW SERVICE CONNECTION AT BHAGULIA PH II, ID304233683 |  |  | BILL/01207/2023-2024 | 270/WBSEDCL-JJM | 24/01/2024 |  | WBSEDCL | 7.24 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Berhampore Mechanical | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16280 | New | NEW SERVICE CONNECTION AT TALBONA , BHAGULIA PH I, ID304233557 |  |  | BILL/01206/2023-2024 | 269/WBSEDCL-JJM | 24/01/2024 |  | WBSEDCL | 12.52 | 0 | 0 | 0
6 | MURSHIDABAD | Burwan | Murshidabad Division | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16280 | New | Formal work order for BHAGULIA & adjoining mouzas PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000805/2022-2023 | 619/MURD | 03/03/2023 | 08/12/2023 | SUMAN ENTERPRISE AND SUMAN AQUA | 183.62 | 91.7 | 49.94 | 50
Total | [13 empty] | 229.19 | 91.7 | 40.01