## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Material Requisition To Resource Division |  |  | RTOR000280/2023-2024 | 1230/MURD/22 | 04/05/2023 | 04/05/2023 | Resource Division | 30.14 | 0 | 0 | 0
2 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Material Requisition To Resource Division |  |  | RTOR000378/2023-2024 | 495/MURD/03 | 15/02/2024 | 15/02/2024 | Resource Division | 9.2 | 0 | 0 | 0
3 | MURSHIDABAD | Raghunathganj-I | Berhampore Mechanical | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Jalangi , Raninagar I and II, Farakka, Raghunathganj I and II block Under District Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000052/2025-2026 | 45/3 | 29/05/2025 | 29/08/2025 | M/S K.P. PRAMANIK | 19.57 | 0 | 0 | 0
4 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Formal work order for GHORSALA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jivan Mission of raghunathganj-I Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000855/2022-2023 | 794/MURD | 21/03/2023 | 01/07/2025 | DHIRENDRANATH MONDAL | 431.52 | 304.81 | 70.64 | 25
5 | MURSHIDABAD | Raghunathganj-I | Berhampore Mechanical | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under GHORSALA ground water based water supply scheme under Block_ Raghunathganj- I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000123/2023-2024 | 3724/MEDB | 03/11/2023 | 01/01/2026 | WEST BENGAL ENGINEERING CO. | 33.53 | 0 | 0 | 30
6 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHORSALA and KASIADANGA ZONE - I Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000370/2023-2024 | 2722/MURD | 29/08/2023 | 19/09/2023 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0 | 0
7 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 5.36 | 2.12 | 100
8 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 28/07/2024 | IMAGIN | 95.53 | 4.29 | 4.49 | 100
Total | [13 empty] | 891.18 | 314.45 | 35.29