## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Material Requisition To Resource Division |  |  | RTOR000280/2023-2024 | 1230/MURD/22 | 04/05/2023 | 04/05/2023 | Resource Division | 30.14 | 0 | 0 | 0
2 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Material Requisition To Resource Division |  |  | RTOR000378/2023-2024 | 495/MURD/03 | 15/02/2024 | 15/02/2024 | Resource Division | 9.2 | 0 | 0 | 0
3 | MURSHIDABAD | Raghunathganj-I | Berhampore Mechanical | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Jalangi , Raninagar I and II, Farakka, Raghunathganj I and II block Under District Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000052/2025-2026 | 45/3 | 29/05/2025 | 29/08/2025 | M/S K.P. PRAMANIK | 19.57 | 0 | 0 | 0
4 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Formal work order for GHORSALA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jivan Mission of raghunathganj-I Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000855/2022-2023 | 794/MURD | 21/03/2023 | 01/07/2025 | DHIRENDRANATH MONDAL | 431.52 | 304.81 | 70.64 | 25
5 | MURSHIDABAD | Raghunathganj-I | Berhampore Mechanical | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under GHORSALA ground water based water supply scheme under Block_ Raghunathganj- I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000123/2023-2024 | 3724/MEDB | 03/11/2023 | 01/01/2026 | WEST BENGAL ENGINEERING CO. | 33.53 | 0 | 0 | 30
6 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHORSALA and KASIADANGA ZONE - I Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000370/2023-2024 | 2722/MURD | 29/08/2023 | 19/09/2023 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0 | 0
7 | MURSHIDABAD | Raghunathganj-I | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. | SM/16281 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 5.36 | 2.12 | 100
Total | [13 empty] | 795.65 | 310.16 | 38.98