## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/16283 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER |  | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 01/12/2022 | STEELCONC AND ASSOCIATES | 16.51 | 5.67 | 34.33 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/16283 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000243/2023-2024 | 1219/MURD/21 | 03/05/2023 | 03/05/2023 | Resource Division | 104.53 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/16283 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV ,Zone-I under Narsinghpur ground water based water supply scheme under Block_ JALANGI Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000072/2023-2024 | 4338/MEDB | 29/12/2023 | 29/03/2024 | B. T. PROJECTS PVT. LTD. | 42.78 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/16283 | Augmentation | Augmentation of NARASINGHAPUR ZONE-I PWSS Laying Distribution System, Rising Main Connection of JALANGI Block, under Murshidabad Division PHE. Dte. PART_A | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000558/2023-2024 | 3219/MURD | 13/10/2023 | 10/04/2024 | M/S UNIVERSAL TRADING | 273.87 | 190.22 | 69.46 | 20
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/16283 | Augmentation | Construction of Pump House, Boundary wall & Providing Functional Household Tap Connection for Augmentation of Narasinghapur Zone-I PWSS in Jalangi Block , Islampur Sub-Division under Murshidabad Division , PHE. Dte. Part-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000588/2023-2024 | 3330/MURD | 23/10/2023 | 20/02/2024 | TRIYA CONSTRUCTION | 105.54 | 27.09 | 25.67 | 30
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/16283 | Augmentation | SHIFTING OF A PORTION OF DHANIRAMPUR 11 KV HTOH LINE ALONG WITH 25KVA DTR FOR NARASINGHAPUR PWSS ID 860315776 |  |  | BILL/01093/2024-2025 |  | 08/11/2024 | 08/11/2024 | WBSEDCL | 3.83 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/16283 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Juginda, Kupila and Narsinghpur Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000109/2022-2023 | 1193/MURD | 10/05/2022 | 29/01/2026 | MAMATA USHA ENTERPRISE | 32.62 | 9.38 | 28.76 | 20
Total | [13 empty] | 579.69 | 232.36 | 40.08