## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | KALGRAM AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16388 | New | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 1075/MURD/4 | 19/04/2023 |  | Resource Division | 20.47 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Berhampore Mechanical | KALGRAM AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16388 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under KALGRAM ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000055/2023-2024 | 1926/MEDB | 16/06/2023 | 14/09/2023 | BHABANI PRASAD MANNA | 21.1 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Berhampore Mechanical | KALGRAM AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16388 | New | NEW SERVICE CONNECTION AT KALGRAM PH 2 ID 304158479 |  |  | BILL/01128/2023-2024 | 216/WBSEDCL-JJM | 05/01/2024 |  | WBSEDCL | 6.37 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Berhampore Mechanical | KALGRAM AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16388 | New | NEW SERVICE CONNECTION AT KALGRAM PH 2 ID 304158479 |  |  | BILL/01128/2023-2024 | 216/WBSEDCL-JJM | 05/01/2024 |  | WBSEDCL | 6.37 | 0 | 0 | 0
5 | MURSHIDABAD | Khargram | Murshidabad Division | KALGRAM AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16388 | New | Formal work order for KALGRAM & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of KHARGRAM Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000850/2022-2023 | 780/MURD | 20/03/2023 | 19/03/2024 | SOFIQUL ISLAM | 329.98 | 54.07 | 16.39 | 20
Total | [13 empty] | 384.3 | 54.07 | 14.07