## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16389 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 1075/MURD/5 | 19/04/2023 | 19/04/2023 | Resource Division | 1.09 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Berhampore Mechanical | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16389 | New | New connection charge for Padamkandi, P/H No.- II. |  |  | BILL/00855/2023-2024 | 121/WBSEDCL-JJM | 27/09/2023 | 27/09/2023 | WBSEDCL | 4.19 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Berhampore Mechanical | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16389 | New | Electric Service New Connection PADAMKANDI PH-1 PWSS Application NO. 3004403540. ID. 304119863 |  |  | BILL/01036/2023-2024 | 171/WBSEDCL-JJM | 05/12/2023 | 05/12/2023 | WBSEDCL | 10.39 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Murshidabad Division | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16389 | New | Allied work of Laying rising main and distribution system with FHTC including Construction Pump House Cum Chlorine Room , Boundary wall at 2nd Tube Well Site and Earth filling at both site of Padamkandi Water Supply Scheme , under Jal Jeevan Mission of KHARGRAM Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000040/2024-2025 | 1926/MURD | 03/07/2024 | 01/09/2024 | ARJIMA CONSTRUCTION | 19.18 | 0 | 0 | 80
5 | MURSHIDABAD | Khargram | Murshidabad Division | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16389 | New | Formal work order for PADAM KANDI & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of KHARGRAM Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000837/2022-2023 | 732/MURD | 15/03/2023 | 02/04/2025 | APURBA SAHA CHOWDHURY | 145.12 | 0 | 0 | 90
6 | MURSHIDABAD | Khargram | Berhampore Mechanical | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16389 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under PADAMKANDI ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000057/2023-2024 | 1927/MEDB | 16/06/2023 | 16/09/2023 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 20.81 | 0 | 0 | 50
Total | [13 empty] | 200.77 | 0 | 0