## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Raghunathganj-II | Murshidabad Division | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. | SM/16391 | New | Formal work order for Khodarampur CT PWSS Construction OHR, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission, Block- Raghunathganj-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000816/2022-2023 | 674/MURD | 09/03/2023 | 08/03/2024 | R.K. CONSTRUCTTION | 227.03 | 0 | 0 | 0
2 | MURSHIDABAD | Raghunathganj-II | Murshidabad Division | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. | SM/16391 | New | Material Requisition To Resource Division |  |  | RTOR000283/2023-2024 | 1230/MURD/25 | 04/05/2023 | 04/05/2023 | Resource Division | 29.19 | 0 | 0 | 0
3 | MURSHIDABAD | Raghunathganj-II | Murshidabad Division | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. | SM/16391 | New | Khodarampur CT PWSS to accommodate FHTC, Laying Distribution System, Rising Main, under Jal Jivan Mission, Block- Raghunathganj-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000894/2022-2023 | 930/MURD | 31/03/2023 | 27/09/2023 | TEKNO ENTERPRISE | 345.69 | 0 | 0 | 0
4 | MURSHIDABAD | Raghunathganj-II | Berhampore Mechanical | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. | SM/16391 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under KHODARAMPUR(CT) ground water based water supply scheme under Block_ Raghunathganj- II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001434/2023-2024 | 4314/MEDB | 29/12/2023 | 29/03/2024 | M/S S. G. ENTERPRISE | 22.57 | 0 | 0 | 0
5 | MURSHIDABAD | Raghunathganj-II | Murshidabad Division | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. | SM/16391 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHODARAMPUR (CT) AND PRASADPUR ZONE-II Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000369/2023-2024 | 2721/MURD | 29/08/2023 | 19/09/2023 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0 | 0
6 | MURSHIDABAD | Raghunathganj-II | Murshidabad Division | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. | SM/16391 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 5.8 | 2.29 | 100
Total | [13 empty] | 896.16 | 5.8 | 0.65