## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | DHANDANGA AMD IT'S ADJOINING MOUJAS | SM/16392 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Dhandanga ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000268/2023-2024 | 3705/MEDB | 03/11/2023 | 03/02/2024 | QUAZI NOZRUL ISLAM | 22.44 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | DHANDANGA AMD IT'S ADJOINING MOUJAS | SM/16392 | New | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 1075/MURD/15 | 19/04/2023 | 19/04/2023 | Resource Division | 14.18 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | DHANDANGA AMD IT'S ADJOINING MOUJAS | SM/16392 | New | Formal Work Order for Laying Distribution System of DHANDANGA PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Murshidabad Circle ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000835/2022-2023 | 741/MURD | 16/03/2023 | 01/04/2025 | APORUPA CONSTRUCTION | 180.78 | 16.43 | 9.09 | 10
4 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | DHANDANGA AMD IT'S ADJOINING MOUJAS | SM/16392 | New | NEW CONNECTION AT DHANDANGA PH-I |  |  | BILL/00233/2024-2025 | 65/WBSEDCL-JJM | 09/05/2024 | 09/05/2024 | WBSEDCL | 4.09 | 0 | 0 | 0
Total | [13 empty] | 221.5 | 16.43 | 7.42