## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | UJUNIA SISUA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16394 | New | Material Requisition To Resource Division |  |  | RTOR000272/2023-2024 | 1230/MURD/15 | 04/05/2023 | 04/05/2023 | Resource Division | 1.09 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | UJUNIA SISUA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16394 | New | BERBARI & UJUNIA adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block-BHARATPUR-I & II of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000873/2022-2023 | 882/MURD | 28/03/2023 | 02/01/2024 | BANAMALI ENTERPRISES | 224.42 | 0 | 0 | 35
3 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | UJUNIA SISUA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16394 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Ujunia Sisua ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000276/2023-2024 | 3717/MEDB | 03/11/2023 | 03/02/2024 | SUNIL RABIDAS | 22.54 | 0 | 0 | 10
4 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | UJUNIA SISUA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16394 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UJUNIA SISUA AND GUNDIRIA Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur I & II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 8 | ORD/000624/2023-2024 | 3409/MURD | 02/11/2023 | 16/02/2025 | GENUINE | 18.43 | 0 | 0 | 100
Total | [13 empty] | 266.48 | 0 | 0