## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | KOLLA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16395 | New | KOLLA PWSS to accommodate FHTC under Jal Jeevan Mission of Block-Bharatpur-I of Kandi Sub Division of Murshidabad District under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 8 | ORD/000018/2023-2024 | 981/MURD | 10/04/2023 | 26/01/2026 | SOM CONSTRUCTION AGENCY | 189.17 | 68.13 | 36.02 | 70
2 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | KOLLA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16395 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Kolla ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000272/2023-2024 | 3710/MEDB | 03/11/2023 | 03/02/2024 | WEST BENGAL ENGINEERING CO. | 22.12 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | KOLLA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16395 | New | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 1075/MURD/13 | 19/04/2023 | 19/04/2023 | Resource Division | 1.38 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | KOLLA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16395 | New | NEW CONNECTION AT KOLLA PH-II |  |  | BILL/01483/2024-2025 | 432/WBSEDCL-JJM | 18/03/2025 | 18/03/2025 | WBSEDCL | 3.57 | 0 | 0 | 0
Total | [13 empty] | 216.24 | 68.13 | 31.51