## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16396 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under AMLAI ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000258/2023-2024 | 3694/MEDB | 03/11/2023 | 03/02/2024 | B. T. PROJECTS PVT. LTD. | 26.12 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16396 | New | Material Requisition To Resource Division |  |  | RTOR000238/2023-2024 | 1219/MURD/26 | 03/05/2023 | 03/05/2023 | Resource Division | 19.9 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16396 | New | Quotation for Amlai PH No-1 |  |  | BILL/01430/2023-2024 | 326/WBSEDCL-JJM | 06/02/2024 | 06/02/2024 | WBSEDCL | 5.41 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16396 | New | Quotation for Amlai PH No-2 |  |  | BILL/01431/2023-2024 | 327/WBSEDCL-JJM | 06/02/2024 | 06/02/2024 | WBSEDCL | 11.27 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16396 | New | Laying Distribution System of AMLAI PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Bharatpur-I Block, Kandi Sub-Division of Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000438/2023-2024 | 2886/MURD | 12/09/2023 | 01/01/2026 | DHIRENDRANATH MONDAL | 591.68 | 327.74 | 55.39 | 10
6 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16396 | New | Allied & Balance Work for Laying of Distribution System, Approach Service Road, Construction of Box Culvert and Land Development of AMLAI PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Bharatpur-I Block, Kandi Sub-Division of Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000735/2023-2024 | 55/MURD | 05/01/2024 | 01/09/2025 | DHIRENDRANATH MONDAL | 53.07 | 28.72 | 54.11 | 10
7 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16396 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at AMLAI and MATHUA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,JUNIOR ENGINEER 5,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000393/2023-2024 | 2795/MURD | 04/09/2023 | 25/09/2023 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0 | 100
Total | [13 empty] | 725.89 | 356.46 | 49.11