## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16397 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000254/2023-2024 | 1219/MURD/39 | 03/05/2023 | 03/05/2023 | Resource Division | 78.66 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16397 | Augmentation | Formal work order for Augmentation of Domkal Zone-I (Part-B) & Domkal Zone - II (Part - A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000828/2022-2023 | 692/MURD | 10/03/2023 | 15/12/2023 | M/S. J. A. CONSTRUCTION | 107.58 | 9.89 | 9.19 | 10
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16397 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,ZONE-II, Part-A under DOMKAL ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000110/2023-2024 | 3718/MEDB | 03/11/2023 | 03/02/2024 | M/S S. R. ENTERPRISE | 33.53 | 0 | 0 | 5
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16397 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 24/09/2023 | MERCHANDISE-INDIA | 26.8 | 4.47 | 16.67 | 100
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16397 | Augmentation | NEW CONNECTION AT DOMKALI Z-II PH-II |  |  | BILL/01110/2024-2025 |  | 14/11/2024 | 14/11/2024 | WBSEDCL | 5.48 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16397 | Augmentation | Domkal Zone-2 PH_1 Application No-3004548731 |  |  | BILL/01229/2023-2024 | 268/WBSEDCL-JJM | 24/01/2024 | 24/01/2024 | WBSEDCL | 5.4 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16397 | Augmentation | Augmentation of Domkal Zone-II (Part-A) Ground Water Based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000055/2023-2024 | 1311/MURD | 11/05/2023 | 12/11/2025 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 593.84 | 362.96 | 61.12 | 10
Total | [13 empty] | 851.29 | 377.31 | 44.32