## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME | SM/16400 | Augmentation | Work of Extension of Existing Boundary Wall and Painting of the same at Birendranagar (Zone-I) Water supply scheme , under Jangipur Sub-Division, P.H.E. Dte in the District Murshidabad. | ASSISTANT ENGINEER |  | ORD/001275/2021-2022 | 392/JSD | 31/12/2021 | 30/01/2022 | S. ROY & CO. | 4.79 | 3.9 | 81.5 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME | SM/16400 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 09/06/2022 | ALLIANCE INDIA | 25.34 | 3.13 | 12.34 | 100
3 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME | SM/16400 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I II & III ,Zone-I under BIRENDRANAGAR ground water based water supply scheme under Block_ Raghunathganj-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000286/2023-2024 | 4346/MEDB | 29/12/2023 | 30/09/2025 | JOGMAYA ENGINEERING | 32 | 0 | 0 | 30
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME | SM/16400 | Augmentation | Laying of Distribution System with FHTC to 752 nos household, Rising Main & OHR Repair of 90 cum capacity for Augmentation of Birendranagar (Zone-I) Pipe water supply scheme in Raghunathganj-II Block under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000865/2022-2023 | 830/MURD | 23/03/2023 | 07/03/2026 | MAA CONSTRUCTION (MUJIBOR, MAJDIYA SEKHPARA) | 103.52 | 92.93 | 89.77 | 30
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME | SM/16400 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000188/2023-2024 | 1210/MURD/21 | 02/05/2023 | 02/05/2023 | Resource Division | 2.46 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME | SM/16400 | Augmentation | Allied works for Renovation of Existing AIRP, Gobordanga Model (Capacity 16 Cu.M/hr) at Birendranagar (Zone-I) W/S Scheme in connection with Augmentation of Birendranagar (Zone-I) PWSS under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000832/2023-2024 | 782/MURD | 14/03/2024 | 03/04/2024 | M/S BAPPA ENTERPRISE | 10.09 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME | SM/16400 | Augmentation | Renovation of Existing AIRP (Capacity 16 Cu.M/hr) for changing of filter media of 1 no Polishing Unit (2.50 m dia x 1.5 m HOS) & 1 no Primary Unit (2.50 m dia x 2.00 m HOS) and painting all vessel, pipes etc. all complete at Birendranagar (Zone-I) W/S Scheme under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000808/2023-2024 | 617/MURD | 28/02/2024 | 29/03/2024 | M/S BAPPA ENTERPRISE | 16.7 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME | SM/16400 | Augmentation | Allied works In connection with Bypass line connection from AIRP to Distribution main at Birendranagar (Zone-I) Water Supply Scheme for the work of Augmentation of Birendranagar (Zone-I) PWSS under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000838/2023-2024 | 821/MURD | 15/03/2024 | 14/04/2024 | MAA CONSTRUCTION (MUJIBOR, MAJDIYA SEKHPARA) | 3.27 | 3.16 | 96.53 | 100
Total | [13 empty] | 198.17 | 103.12 | 52.03