## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16402 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 1147/MURD/6 | 27/04/2023 | 27/04/2023 | Resource Division | 0.55 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16402 | Augmentation | NEW CONNECTION PRASADPUR Z-III PH-I |  |  | BILL/01488/2023-2024 | 395/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 3.71 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16402 | Augmentation | PRASADPUR Z-III PH-II |  |  | BILL/01486/2023-2024 | 394/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 3.78 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16402 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2,Junior Engineer 3,JUNIOR ENGINEER 6 | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 12/10/2024 | BIJAY CHOWDHURY | 2120.16 | 56.38 | 2.66 | 5
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16402 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for PRASADPUR ZONE-III Ground Based Water Supply Scheme in Suti-II Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000051/2025-2026 | 1226/MURD | 28/05/2025 | 27/07/2025 | INDRAJIT DUBEY | 19.62 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16402 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 09/06/2022 | RADIANT | 73.97 | 3.05 | 4.12 | 100
Total | [13 empty] | 2221.78 | 59.42 | 2.67