## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHULA PWSS BELDANGA -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16406 | Augmentation | Construction of 450 Cum OHR, Pump House with sanitary and Water Supply Arrangement , Pump House cum Blower room And Boundary Wall for Augmentation work MAHULA of Beldanga -I Block under Murshidabad Division , PHE.Dte. PART_B | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000234/2023-2024 | 2405/MURD | 07/08/2023 | 06/08/2024 | ABHISHEK BHATTACHARYA | 198.86 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHULA PWSS BELDANGA -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16406 | Augmentation | Providing FHTC Connection to 3199 nos household , Laying of Distribution System, Rising Main for Augmentation work MAHULA of Beldanga -I Block under Murshidabad Division , PHE.Dte. PART _A. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000246/2023-2024 | 2467/MURD | 09/08/2023 | 05/02/2024 | SARAJIT KUMAR MAJUMDER | 306.82 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHULA PWSS BELDANGA -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16406 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (MOHULA PWSS Scheme, Block - Beldanga-I) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. |  | JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | ORD/000840/2021-2022 | 3273/MURD | 05/10/2021 | 04/12/2021 | RADIANT | 10.24 | 10.24 | 100 | 1
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHULA PWSS BELDANGA -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16406 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000218/2023-2024 | 1290/MURD/02 | 03/05/2023 | 03/05/2023 | Resource Division | 0.41 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHULA PWSS BELDANGA -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/16406 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 3.29 | 3.37 | 80
Total | [13 empty] | 613.82 | 13.53 | 2.2