## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Central Drilling | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16409 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16409 | Augmentation | Augmentation of MURADPUR JALANGI ZONE-III /Tenya Zone-II & Zone-III PWSS Laying Distribution System, of JALANGI /Bharatpur-II Block , under Murshidabad Division PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 8,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000375/2023-2024 | 2755/MURD | 01/09/2023 | 21/08/2025 | ULTRA CONSTRUCTION. | 100.45 | 0 | 0 | 95
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16409 | Augmentation | Laying of Rising main , Distribution System, FHTC, OHR Repairing (Capacity 600 cum), , Sinking of Tube Well , Construction of pump house & Boundary wall and approach road for Augmentation of Tenya Zone-III PWSS in Bharatpur-II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,JUNIOR ENGINEER 8 | ORD/000613/2023-2024 | 3375/MURD | 31/10/2023 | 01/01/2026 | H.ENTERPRISE | 499.38 | 23.42 | 4.69 | 53
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16409 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 1004/MURD/A | 11/04/2023 | 11/04/2023 | Resource Division | 122.58 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16409 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 1004/MURD/7 | 11/04/2023 | 11/04/2023 | Resource Division | 42.04 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16409 | Augmentation | RESTORATION OF DAMAGED ROAD CAUSE TO LAYING OF WATER SUPPLY PIPELINE ON SALAR TALIBPUR ROAD FROM 1.80 KMP TO 4.2 KMP UNDER MURSHIDABD HIGHWAY DIVN-II. |  |  | BILL/01632/2024-2025 | 600-MSD/2024-25 | 16/12/2024 | 16/12/2024 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 22.81 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16409 | Augmentation | Continuation Work Order for the work of Hiring of Maxi cab (Non- Air Condition, Bharat Stage III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months i.e. 28.02.2025 TO 31.07.2025. VEHICLE NO - WB57F2352 | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000474/2024-2025 | 41/KSD | 25/02/2025 | 25/07/2025 | H.MONDAL CONSTRUCTION | 0.87 | 1.2 | 138.33 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16409 | Augmentation | Continuation Work Order for the work of Hiring of Maxi cab (Non- Air Condition, Bharat Stage III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months i.e. 01.08.2025 TO 31.12.2025. VEHICLE NO - WB57F2352 | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000097/2025-2026 | 97/KSD | 17/07/2025 | 14/12/2025 | H.MONDAL CONSTRUCTION | 0.87 | 0 | 0 | 0
Total | [13 empty] | 22128.76 | 24.62 | 0.11