## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16410 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000260/2023-2024 | 1230/MURD/08 | 04/05/2023 | 04/05/2023 | Resource Division | 19.32 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16410 | Augmentation | Repair work of concrete road between node point 52-53 at Godapara of Panchthupi Zone -III Piped Water Supply Scheme under Jal Jeevan Mission under Kandi Sub Division, P.H.Engineering Dte. in the district of Murshidabad. |  |  | ORD/000158/2024-2025 | 149/KSD | 28/10/2024 | 27/11/2024 | M/S BHUBAN DAS | 0.96 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16410 | Augmentation | Repair work of concrete road between node point 28-41-45-50 at Godapara of Panchthupi Zone -III Piped Water Supply Scheme under Jal Jeevan Mission under Kandi Sub Division, P.H.Engineering Dte. in the district of Murshidabad |  |  | ORD/000159/2024-2025 | 150/KSD | 28/10/2024 | 27/11/2024 | M/S BHUBAN DAS | 0.97 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16410 | Augmentation | ADDITIONAL QTN FOR PANCHTHUPI ZONE III PHI |  |  | BILL/00898/2024-2025 |  | 06/09/2024 | 06/09/2024 | WBSEDCL | 7.3 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16410 | Augmentation | POWER CONNECTION AT PWSS PH1 Z3 PANCHTHUPI ID 304256293 |  |  | BILL/00184/2024-2025 | 39/WBSEDCL-JJM | 22/04/2024 | 22/04/2024 | WBSEDCL | 10.15 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16410 | Augmentation | POWER CONNECTION AT PWSS PH 2 Z 3 PANCHTHUPI ID 304256294 |  |  | BILL/00185/2024-2025 | 40/WBSEDCL-JJM | 22/04/2024 | 22/04/2024 | WBSEDCL | 7.1 | 0 | 0 | 0
Total | [13 empty] | 45.81 | 0 | 0