## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16411 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 04/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 1.91 | 2.14 | 76
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16411 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000259/2023-2024 | 1230/MURD/02 | 04/05/2023 | 04/05/2023 | Resource Division | 36.51 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16411 | Augmentation | Electric Service Connection at SABARMBATI PWSS ph ii, Application NO.3004494928, ID 304193739 |  |  | BILL/01081/2023-2024 | 187/WBSEDCL-JJM | 19/12/2023 | 19/12/2023 | WBSEDCL | 4.81 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16411 | Augmentation | NEW SERVICE CONNECTION AT PWSS PANCHTHUPI PH 1 Z2 ID 304247057 |  |  | BILL/01421/2023-2024 | 313/WBSEDCL-JJM | 05/02/2024 | 05/02/2024 | WBSEDCL | 7.38 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16411 | Augmentation | NEW SERVICE CONNECTION AT PWSS PANCHTHUPI PH3 Z2 ID 304247149 |  |  | BILL/01423/2023-2024 | 325/WBSEDCL-JJM | 06/02/2024 | 06/02/2024 | WBSEDCL | 7.28 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16411 | Augmentation | Formal work order for Augmentation of PANCHTHUPI ZONE-II PWSS to accommodate FHTC , under Jal Jeevan Mission, Block- BURWAN of Kandi Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000814/2022-2023 | 672/MURD | 09/03/2023 | 08/10/2026 | IMRAN CONSTRUCTION | 416.51 | 197.28 | 47.37 | 85
7 | MURSHIDABAD |  | Central Drilling | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. | SM/16411 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 34.41 | 0.16 | 11
Total | [13 empty] | 21901.53 | 233.61 | 1.07