## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. | SM/16412 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1004/MURD/1 | 11/04/2023 | 11/04/2023 | Resource Division | 13.32 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. | SM/16412 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 2.62 | 2.69 | 80
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. | SM/16412 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II under Simulia Jaulia ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000242/2023-2024 | 3678/MEDB | 03/11/2023 | 01/01/2026 | SARKAR CONSTRUCTION | 21.39 | 16.4 | 76.68 | 15
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. | SM/16412 | Augmentation | Augmentation of Ground Water Based SIMULIA & JAULIA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- BHARATPUR-II of Kandi Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000587/2023-2024 | 3322/MURD | 22/10/2023 | 01/08/2025 | VISION ENTERPRISE | 355.14 | 0 | 0 | 10
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. | SM/16412 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional HouseHold Connection of different existing PWSS (SIMULIA & JAMULIA PWSS Scheme, Block- BHARATPUR-II to be Augmentation/Rejuvination under Murshidabad Division P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000822/2021-2022 | 3261/MURD | 05/10/2021 | 04/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.78 | 2.97 | 51.38 | 1
Total | [13 empty] | 493.11 | 21.99 | 4.46