## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- II A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16415 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 09/06/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 7.75 | 20.51 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- II A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16415 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 12/11/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- II A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16415 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Sankopara halt Station (TP NO 244/5 & 244/6) at Monrajpur mouza & Connecting with existing 110 mm dia uPVC distribution main line of Mahadevnagar Zone - II ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000421/2021-2022 | 2477/MURD | 16/08/2021 | 15/10/2021 | ACQUA CONSTRACTION CONSORTIAM | 23.65 | 21.37 | 90.39 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- II A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16415 | Augmentation | LAND LEASE FEE CHARGES(IR-LSPS) |  |  | BILL/00592/2025-2026 |  | 23/09/2025 | 23/09/2025 | EASTERN RAILWAY (MALDA DIVISION) | 30.1 | 0 | 0 | 0
5 | MURSHIDABAD |  | Central Drilling | Augmentation of Mahadebnagar Zone- II A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16415 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- II A Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16415 | Augmentation | Laying of Distribution System, FHTC, construction of OHR (Capacity 300 & 400 cum), Sinking of Tube Well , and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of MAHADEBNAGAR ZONE- IA,IB,IC ,IIA & IIB PWSS in Farakka Block, Murshidabad District under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000790/2023-2024 | 441/MURD | 08/02/2024 | 01/01/2027 | MACKINTOSH BURN LIMITED | 1715.31 | 40.17 | 2.34 | 36
Total | [13 empty] | 23181.55 | 69.29 | 0.3