## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- II B Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16416 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 12/11/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
2 | MURSHIDABAD |  | Central Drilling | Augmentation of Mahadebnagar Zone- II B Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16416 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahadebnagar Zone- II B Water Supply Scheme Block - Farakka, Dist- Murshidabad. | SM/16416 | Augmentation | Laying of Distribution System, FHTC, construction of OHR (Capacity 300 & 400 cum), Sinking of Tube Well , and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of MAHADEBNAGAR ZONE- IA,IB,IC ,IIA & IIB PWSS in Farakka Block, Murshidabad District under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000790/2023-2024 | 441/MURD | 08/02/2024 | 01/01/2026 | MACKINTOSH BURN LIMITED | 1715.31 | 0 | 0 | 36
Total | [13 empty] | 23090.04 | 0 | 0