## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/16419 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-II under Rejinagar ground water based water supply scheme under Block_ Beldanga_II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000237/2023-2024 | 3673/MEDB | 03/11/2023 | 03/02/2024 | MASSK ENGINEERING WORKS | 22.62 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/16419 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000137/2023-2024 | 1167/MURD/42 | 28/04/2023 | 28/04/2023 | Resource Division | 34.04 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/16419 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000281/2023-2024 | 2657/MURD | 24/08/2023 | 13/09/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 2.58 | 12.95 | 100
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/16419 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2024-2025 | 1811/MURD/20 | 20/06/2024 | 20/06/2024 | Resource Division | 5.36 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/16419 | Augmentation | Augmentation of Ground Water Based Rejinagar Zone II PWSS of accommodate with Switch Room, Boundary Wall, 300 CUM OHR in Beldanga II Block within Murshidabad District under Murshidabad Division, PHE Dte. [ Part B ] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000583/2023-2024 | 3318/MURD | 22/10/2023 | 18/04/2025 | MODERN CONSTRUCTION | 163.25 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/16419 | Augmentation | Providing FHTC Connection to 870 nos household , Laying of Distribution System, Rising Main for Augmentation work of Rejinagar Zone-II PWSS within Beldanga-II Block under Murshidabad Division , PHE.Dte. ( PART - A) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000582/2023-2024 | 3317/MURD | 22/10/2023 | 02/04/2025 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 195.25 | 59.36 | 30.4 | 85
Total | [13 empty] | 440.47 | 61.95 | 14.06