## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Salar Zone- II B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16424 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II ,Zone-IIB under Salar ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000240/2023-2024 | 3676/MEDB | 03/11/2023 | 02/02/2025 | DAS ENTERPRISE (CHOA) | 21.42 | 3.85 | 17.96 | 8
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Salar Zone- II B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16424 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I , II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone- II B Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Bharatpur - II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000696/2023-2024 | 3781/MURD | 11/12/2023 | 01/01/2024 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Salar Zone- II B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16424 | Augmentation | Sinking of 01 (One) No of 250mm x 150 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHAYRAMARI Part-A and Salar Zone - IIB Water Supply Scheme as required under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5,JUNIOR ENGINEER_JALANGI BLOCK | ORD/000103/2023-2024 | 1744/MURD | 06/07/2023 | 20/07/2023 | SARKAR WATER SUPPLY AGENCY | 9.22 | 7.39 | 80.14 | 100
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Salar Zone- II B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16424 | Augmentation | NEW CONNECTION AT SALAR Z-II/B PH-I |  |  | BILL/01221/2024-2025 | 299/WBSEDCL-JJM | 06/12/2024 | 06/12/2024 | WBSEDCL | 6.15 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Salar Zone- II B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. | SM/16424 | Augmentation | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,Junior Engineer 3,JUNIOR ENGINEER 5 | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 01/01/2026 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 0 | 20
Total | [13 empty] | 125.98 | 11.24 | 8.92