## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KUSUMGACHI PIPED WATER SUPPLY SCHEME. | SM/16427 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000199/2023-2024 | 1210/MURD/05 | 02/05/2023 | 02/05/2023 | Resource Division | 50.19 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KUSUMGACHI PIPED WATER SUPPLY SCHEME. | SM/16427 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 18/08/2022 | M/S SOBHA & CO. | 9.79 | 0 | 0 | 10
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KUSUMGACHI PIPED WATER SUPPLY SCHEME. | SM/16427 | Augmentation | Providing FHTC Connection to 800 nos household, Laying of Rising Main, Laying of Distribution System, Overhauling of RCC 180 Cum OHR, Construction Pump House with sanitary and Water Supply Arrangement (T/W-I), Special repair and renovation of existing 1 (One) Nos Pump House and Alied Works, Construction of Boundary Wall, Repair of Boundary Wall & Construction of RCC approach road for Augmentation of KUSUMGACHI Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000880/2022-2023 | 904/MURD | 29/03/2023 | 26/08/2025 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 174.93 | 35.35 | 20.21 | 50
4 | MURSHIDABAD |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED KUSUMGACHI PIPED WATER SUPPLY SCHEME. | SM/16427 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KUSUMGACHI PIPED WATER SUPPLY SCHEME. | SM/16427 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for KUSUMGACHI Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000023/2025-2026 | 982/MURD | 02/05/2025 | 01/07/2025 | M/S SAJAHAN CHOWDHURY | 22.96 | 0 | 0 | 0
Total | [13 empty] | 21597.64 | 35.35 | 0.16