## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Berhampore Mechanical | KHORDDA NARAYANPUR PIPED WATER SUPPLY SCHEME, BLOCK- KANDI , DISTRICT- MURSHIDABAD. | SM/16442 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Khordda Narayanpur Part-A village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000206/2023-2024 | 3066/MEDB | 02/08/2023 | 02/11/2023 | M/S SAJAHAN CHOWDHURY | 6.27 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Berhampore Mechanical | KHORDDA NARAYANPUR PIPED WATER SUPPLY SCHEME, BLOCK- KANDI , DISTRICT- MURSHIDABAD. | SM/16442 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Khordda Narayanpur Part-B village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000207/2023-2024 | 3067/MEDB | 02/08/2023 | 02/11/2023 | JOY BISHNU ENGINEERING CO. | 6.3 | 0 | 0 | 0
3 | MURSHIDABAD | Kandi | Murshidabad Division | KHORDDA NARAYANPUR PIPED WATER SUPPLY SCHEME, BLOCK- KANDI , DISTRICT- MURSHIDABAD. | SM/16442 | New | Ground Water based piped water supply scheme for Khordda Narayanpur Part- B village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000237/2023-2024 | 2340/MURD | 03/08/2023 | 02/10/2023 | CHOWDHURY CONSTRUCTION | 30.55 | 0 | 0 | 0
4 | MURSHIDABAD | Kandi | Murshidabad Division | KHORDDA NARAYANPUR PIPED WATER SUPPLY SCHEME, BLOCK- KANDI , DISTRICT- MURSHIDABAD. | SM/16442 | New | Ground Water based piped water supply scheme for Khordda Narayanpur Part- A village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000257/2023-2024 | 2493/MURD | 11/08/2023 | 10/10/2023 | M/S GREAT INDIA CONSTRUCTION | 30.54 | 0 | 0 | 0
Total | [13 empty] | 73.66 | 0 | 0