## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | NEW CONNECTION AT JAULIA PH-II |  |  | BILL/00232/2024-2025 | 64/WBSEDCL-JJM | 09/05/2024 | 09/05/2024 | WBSEDCL | 3.29 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | NEW CONNECTION AT JAULIA PH-I |  |  | BILL/00246/2024-2025 | 77/WBSEDCL-JJM | 20/05/2024 | 20/05/2024 | WBSEDCL | 4.25 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | Ground Water based piped water supply scheme for Jaulia Part- B village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000219/2023-2024 | 2328/MURD | 02/08/2023 | 30/04/2026 | SARTHAK SK. | 30.55 | 16.8 | 55 | 25
4 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | Ground Water based piped water supply scheme for Jaulia Part- C village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000220/2023-2024 | 2339/MURD | 03/08/2023 | 01/05/2026 | MAHATO ENTERPRISE | 30.55 | 18.22 | 59.63 | 100
5 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Pump House No. II under JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II and KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000017/2025-2026 | 1141/MEDB | 14/05/2025 | 05/06/2026 | M/S K.P. PRAMANIK | 11.64 | 0 | 0 | 20
6 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000541/2024-2025 | 327/MEDB | 10/02/2025 | 30/05/2026 | M/S K.P. PRAMANIK | 11.64 | 0 | 0 | 100
7 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | Ground Water based piped water supply scheme for Jaulia Part- A village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000215/2023-2024 | 2330/MURD | 02/08/2023 | 01/03/2026 | MADAN MOHAN SASMAL | 30.55 | 24.45 | 80.03 | 20
Total | [13 empty] | 122.46 | 59.47 | 48.56