## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aurangabad Zone-I Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/16456 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 3.68 | 4.52 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aurangabad Zone-I Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/16456 | Augmentation | Laying Distribution System, Rising Main Connection, FHTC connections, Construction of 2 Nos Pump House Room, 100 Mtr Boundary Wall, for Augmentation of Aurangabad Zone-I PWSS of Suti-II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000088/2025-2026 | 1510/MURD | 03/07/2025 | 01/10/2025 | H.I.ENTERPRISE | 133.86 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aurangabad Zone-I Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/16456 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Jangipur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(83 Nos.) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000134/2024-2025 | 2636/MURD | 23/09/2024 | 13/10/2024 | KUNTAL SAHA | 9.28 | 0 | 0 | 100
4 | MURSHIDABAD |  | Central Drilling | Augmentation of Aurangabad Zone-I Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/16456 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 18.67 | 0.09 | 11
Total | [13 empty] | 21564.34 | 22.35 | 0.1