## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SYAMPUR AND ADJOINING MOUJAS PWSS | SM/16475 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1075/MURD/6 | 19/04/2023 | 19/04/2023 | Resource Division | 10.59 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | SYAMPUR AND ADJOINING MOUJAS PWSS | SM/16475 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Syampur ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000168/2023-2024 | 2091/MEDB | 19/06/2023 | 19/09/2023 | ARINDAM MAJUMDAR | 21.72 | 0 | 0 | 15
3 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | SYAMPUR AND ADJOINING MOUJAS PWSS | SM/16475 | New | Shyampur PH-1 Application no- 300454852 |  |  | BILL/01176/2023-2024 | 234/WBSEDCL-JJM | 15/01/2024 | 15/01/2024 | WBSEDCL | 5.34 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SYAMPUR AND ADJOINING MOUJAS PWSS | SM/16475 | New | Formal work order for SYAMPUR & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of BURWAN Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000858/2022-2023 | 803/MURD | 22/03/2023 | 01/01/2026 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 448.94 | 0 | 0 | 75
Total | [13 empty] | 486.6 | 0 | 0