## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SYAMPUR AND ADJOINING MOUJAS PWSS | SM/16475 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1075/MURD/6 | 19/04/2023 | 19/04/2023 | Resource Division | 10.59 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | SYAMPUR AND ADJOINING MOUJAS PWSS | SM/16475 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Syampur ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000168/2023-2024 | 2091/MEDB | 19/06/2023 | 19/09/2023 | ARINDAM MAJUMDAR | 21.72 | 17.52 | 80.68 | 15
3 | MURSHIDABAD | Bharatpur-I | Berhampore Mechanical | SYAMPUR AND ADJOINING MOUJAS PWSS | SM/16475 | New | Shyampur PH-1 Application no- 300454852 |  |  | BILL/01176/2023-2024 | 234/WBSEDCL-JJM | 15/01/2024 | 15/01/2024 | WBSEDCL | 5.34 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur-I | Murshidabad Division | SYAMPUR AND ADJOINING MOUJAS PWSS | SM/16475 | New | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Kandi Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(89 Nos.) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000133/2024-2025 | 2635/MURD | 23/09/2024 | 01/07/2025 | SABSAMAY | 9.85 | 0 | 0 | 80
Total | [13 empty] | 47.5 | 17.52 | 36.89