## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Berhampore Mechanical | ROSORA(P) PIPED WATER SUPPLY SCHEME , BLOCK- KANDI , DISTRICT- MURSHIDABAD. | SM/16504 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Rosora (P) Part-A village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000208/2023-2024 | 3068/MEDB | 02/08/2023 | 02/11/2023 | DAS ENTERPRISE (CHOA) | 6.3 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Berhampore Mechanical | ROSORA(P) PIPED WATER SUPPLY SCHEME , BLOCK- KANDI , DISTRICT- MURSHIDABAD. | SM/16504 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Rosora (P) Part-B village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000209/2023-2024 | 3069/MEDB | 02/08/2023 | 02/11/2023 | A. S. ENGINEERING | 6.32 | 0 | 0 | 0
3 | MURSHIDABAD | Kandi | Murshidabad Division | ROSORA(P) PIPED WATER SUPPLY SCHEME , BLOCK- KANDI , DISTRICT- MURSHIDABAD. | SM/16504 | New | Ground Water based piped water supply scheme for Rosora (P) Part- A village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000241/2023-2024 | 2423/MURD | 08/08/2023 | 07/10/2023 | C. R. CONSTRUCTION | 30.55 | 0 | 0 | 0
4 | MURSHIDABAD | Kandi | Murshidabad Division | ROSORA(P) PIPED WATER SUPPLY SCHEME , BLOCK- KANDI , DISTRICT- MURSHIDABAD. | SM/16504 | New | Ground Water based piped water supply scheme for Rosora (P) Part- B village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000239/2023-2024 | 2417/MURD | 08/08/2023 | 01/04/2026 | SUKUMAR ROY | 30.55 | 0 | 0 | 50
Total | [13 empty] | 73.72 | 0 | 0