## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur - I | Murshidabad Division | MASLA AND ADJOINING MOUJAS PWSS | SM/16529 | New | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 1075/MURD/14 | 19/04/2023 |  | Resource Division | 1.09 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur - I | Central Drilling | MASLA AND ADJOINING MOUJAS PWSS | SM/16529 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). |  |  | ORD/000209/2023-2024 | 2203/CDD | 01/03/2024 | 29/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | MASLA AND ADJOINING MOUJAS PWSS | SM/16529 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under MASLA ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000165/2023-2024 | 2089/MEDB | 19/06/2023 | 17/09/2023 | M/S S. S. ENTERPRISE (DOMKAL) | 21.56 | 7.95 | 36.87 | 10
4 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | MASLA AND ADJOINING MOUJAS PWSS | SM/16529 | New | MASLA PH-1 |  |  | BILL/01508/2023-2024 | 392/WBSEDCL-JJM | 04/03/2024 |  | WBSEDCL | 4.25 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | MASLA AND ADJOINING MOUJAS PWSS | SM/16529 | New | MASLA PH-1 |  |  | BILL/01508/2023-2024 | 392/WBSEDCL-JJM | 04/03/2024 |  | WBSEDCL | 4.25 | 0 | 0 | 0
6 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | MASLA AND ADJOINING MOUJAS PWSS | SM/16529 | New | MASLA PH-2 |  |  | BILL/01509/2023-2024 | 393/WBSEDCL-JJM | 04/03/2024 |  | WBSEDCL | 4.28 | 0 | 0 | 0
7 | MURSHIDABAD | Bharatpur - I | Murshidabad Division | MASLA AND ADJOINING MOUJAS PWSS | SM/16529 | New | MASLA PWSS under Jal Jeevan Mission of BHARATPUR - I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000188/2023-2024 | 1996/MURD | 21/07/2023 | 16/05/2024 | A.K. INSDUSTRIES | 239.5 | 0 | 0 | 30
Total | [13 empty] | 385.98 | 7.95 | 2.06