## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/16544 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Raghunathganj-II of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Giriya Kismat Water supply Scheme, Jotsundar Water Supply Scheme, Giria Water Supply Scheme Zone-I & II. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000562/2022-2023 | 2912/MURD | 01/11/2022 | 01/12/2022 | STEELCONC AND ASSOCIATES | 12.39 | 2.48 | 19.99 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/16544 | Augmentation | Augmentation of Ground Water Based GIRIA KISMAT PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6 | ORD/000009/2023-2024 | 951/MURD | 05/04/2023 | 01/01/2026 | SUNRISE CONSTRUCTION | 354.38 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/16544 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000264/2023-2024 | 1230/MURD/05 | 04/05/2023 | 04/05/2023 | Resource Division | 46.51 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/16544 | Augmentation | NEW SERVICE CONNECTION AT GIRIA KISMAT PH 2 ID 304514056 |  |  | BILL/01218/2024-2025 |  | 02/12/2024 | 02/12/2024 | WBSEDCL | 7 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/16544 | Augmentation | EW SERVICE CONNECTION AT GIRIA KISMAT PH 2 ID 304514056 |  |  | BILL/01224/2024-2025 | 297/WBSEDCL-JJM | 11/12/2024 | 11/12/2024 | WBSEDCL | 7 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/16544 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. under MEDB, PHE Dte." | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000568/2024-2025 | 383/MEDB | 12/02/2025 | 12/05/2025 | SUNIL RABIDAS | 34.09 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. | SM/16544 | Augmentation | NEW SERVICE CONNECTION AT GIRIA KISMAT PH 1 (NEW) C ID 304514057 |  |  | BILL/01343/2024-2025 | 386/WBSEDCL-JJM | 10/02/2025 | 10/02/2025 | WBSEDCL | 10.77 | 0 | 0 | 0
Total | [13 empty] | 472.13 | 2.48 | 0.52