## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -B Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16546 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 24/09/2023 | MERCHANDISE-INDIA | 26.8 | 0 | 0 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -B Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16546 | Augmentation | Augmentation of SHIBNAGAR LASKARPUR (Zone-I) Part-B & Garibpur (Zone-I) Part-B PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 | ORD/000440/2023-2024 | 2888/MURD | 12/09/2023 | 01/10/2025 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 226.15 | 0 | 0 | 75
Total | [13 empty] | 252.95 | 0 | 0