## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aurangabad Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/16547 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 0 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aurangabad Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/16547 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000222/2023-2024 | 1219/MURD/08 | 03/05/2023 | 03/05/2023 | Resource Division | 47.69 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aurangabad Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/16547 | Augmentation | Augmentation Work of Aurangabad Zone-II Piped Water Supply Scheme to accommodate with FHTC (586 Nos), Laying of Rising Main , Laying of Distribution System , construction of 600 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000294/2023-2024 | 2668/MURD | 24/08/2023 | 23/08/2024 | KUNDU CONSTRUCTION | 371.15 | 0 | 0 | 0
4 | MURSHIDABAD |  | Central Drilling | Augmentation of Aurangabad Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/16547 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aurangabad Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. | SM/16547 | Augmentation | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month].For the month of 17/01/2025 to 16/07/2025. [ Vehicle No:- WB 58 CD 3758] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000244/2024-2025 | 15/JSD | 17/01/2025 | 17/07/2025 | HASSAN CONSTRUCTION | 0.88 | 0 | 0 | 0
Total | [13 empty] | 21840.92 | 0 | 0