## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti-II | Berhampore Mechanical | BAURIPUNI PIPED WATER SUPPLY SCHEME. | SM/16551 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BAURIPUNI ground water based water supply scheme under Block_ Suti_II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000086/2023-2024 | 1900/MEDB | 16/06/2023 | 16/09/2023 | DAS ENTERPRISE ( MANGO LANE) | 33.5 | 0 | 0 | 0
2 | MURSHIDABAD | Suti-II | Murshidabad Division | BAURIPUNI PIPED WATER SUPPLY SCHEME. | SM/16551 | New | Material Requisition To Resource Division |  |  | RTOR000288/2023-2024 | 1230/MURD/30 | 04/05/2023 | 04/05/2023 | Resource Division | 21.71 | 0 | 0 | 0
3 | MURSHIDABAD | Suti-II | Murshidabad Division | BAURIPUNI PIPED WATER SUPPLY SCHEME. | SM/16551 | New | Formal work order for BAURIPUNI PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000851/2022-2023 | 788/MURD | 21/03/2023 | 20/03/2024 | KISMAT ARA BEGAM | 355.05 | 0 | 0 | 10
4 | MURSHIDABAD | Suti-II | Murshidabad Division | BAURIPUNI PIPED WATER SUPPLY SCHEME. | SM/16551 | New | Material Requisition To Resource Division |  |  | RTOR000381/2023-2024 | 495/MURD/13 | 15/02/2024 | 15/02/2024 | Resource Division | 7.53 | 0 | 0 | 0
5 | MURSHIDABAD | Suti-II | Berhampore Mechanical | BAURIPUNI PIPED WATER SUPPLY SCHEME. | SM/16551 | New | NEW CONNECTION BAURIPUNI PH-II |  |  | BILL/01482/2023-2024 | 390/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 11.71 | 0 | 0 | 0
6 | MURSHIDABAD | Suti-II | Berhampore Mechanical | BAURIPUNI PIPED WATER SUPPLY SCHEME. | SM/16551 | New | BAURIPUNI PH-1 NEW CONNECTION |  |  | BILL/01483/2023-2024 | 391/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 3.47 | 0 | 0 | 0
7 | MURSHIDABAD | Suti-II | Murshidabad Division | BAURIPUNI PIPED WATER SUPPLY SCHEME. | SM/16551 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 0 | 0 | 100
Total | [13 empty] | 686.21 | 0 | 0