## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JURANPUR PIPE WATER SUPPLY SCHEME (PART-B) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16558 | Augmentation | Augmentation of JURANPUR (Part-B) PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000080/2023-2024 | 1382/MURD | 22/05/2023 | 01/01/2026 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 122.02 | 30.68 | 25.14 | 50
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JURANPUR PIPE WATER SUPPLY SCHEME (PART-B) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16558 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 24/09/2023 | MERCHANDISE-INDIA | 26.8 | 4.47 | 16.67 | 100
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JURANPUR PIPE WATER SUPPLY SCHEME (PART-B) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16558 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Juranpur ( PART-B) Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000128/2023-2024 | 1765/MURD | 06/07/2023 | 27/07/2023 | NADIA TUBEWELLS | 35.34 | 31.71 | 89.74 | 80
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF JURANPUR PIPE WATER SUPPLY SCHEME (PART-B) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16558 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000151/2023-2024 | 1180/MURD/01 | 29/04/2023 | 29/04/2023 | Resource Division | 1.11 | 0 | 0 | 0
Total | [13 empty] | 185.27 | 66.86 | 36.09