## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-I) PIPED WATER SUPPLY SCHEME. | SM/16566 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 18/08/2022 | APEX ENGINEERING | 10.79 | 0.53 | 4.9 | 100
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-I) PIPED WATER SUPPLY SCHEME. | SM/16566 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Barabil Raghunathpur Water Supply Scheme of TW-I under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000592/2022-2023 | 3062/MURD | 17/11/2022 | 17/12/2022 | GENUINE | 11.75 | 8.53 | 72.63 | 100
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-I) PIPED WATER SUPPLY SCHEME. | SM/16566 | Augmentation | Augmentation of Ground Water Based Barabil Raghunathpur zone-I PWSS to accommodate FHTC of 105 nos household, Laying Distribution System, Laying Rising Main , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works,Repair of Boundary Wall at T/W-I site & T/W-II site &Overhauling of R.C.C. elevated reservoir 350 Cum capacity of staging hight 20 mtr. for Barabil Raghunathpur ( ZONE-I ) Ground water based Piped water supply scheme at Jalangi Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000600/2023-2024 | 3355/MURD | 30/10/2023 | 17/04/2026 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 155.66 | 0 | 0 | 30
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-I) PIPED WATER SUPPLY SCHEME. | SM/16566 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000161/2023-2024 | 1180/MURD/31 | 29/04/2023 | 29/04/2023 | Resource Division | 55.46 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-I) PIPED WATER SUPPLY SCHEME. | SM/16566 | Augmentation | Continuation work order for Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol, Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Zone-II Water Supply Scheme, Garaimari Zone-II Water Supply Scheme, Islampur Zone-II Water Supply Scheme, Barabil Raghunathpur Zone-III Water Supply Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000131/2024-2025 | 2673/MURD | 25/09/2024 | 25/10/2024 | APEX ENGINEERING | 10.12 | 0 | 0 | 100
Total | [13 empty] | 243.78 | 9.06 | 3.72