## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. | SM/16622 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C |  | JUNIOR ENGINEER 1,JUNIOR HARIHARPARA BLOCK | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 04/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. | SM/16622 | Augmentation | Balance and allied works for providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission) and under command area of village of GHORAMARA (Village Code -315515) under Ghoramara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000165/2022-2023 | 154/BSD | 12/04/2022 | 12/05/2022 | M/S M.S. ENTERPRISE | 4.69 | 4.59 | 97.72 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. | SM/16622 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER |  | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 24/09/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. | SM/16622 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under GHORAMARA ground water based water supply scheme under Block_ NAWDA Dist. - Murshidabad under MEDB, PHE Dte. |  |  | ORD/000671/2023-2024 | 4347/MEDB | 29/12/2023 | 28/03/2024 | BHABANI PRASAD MANNA | 33.55 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. | SM/16622 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen(RDS) filter at GHORAMARA Water Supply Scheme atHead Work Site, 2nd Site site at Nawda Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000116/2023-2024 | 1760/MURD | 06/07/2023 | 27/07/2023 | SUJIT KUMAR SAHA | 18.45 | 6.49 | 35.16 | 100
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. | SM/16622 | Augmentation | Providing FHTC Connection to 176 nos household ,Construction of 200 Cum OHR, Rising Main , for Augmentation work of GHORAMARA PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. (part_A) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000882/2022-2023 | 906/MURD | 22/03/2023 | 21/03/2024 | PRATICHI ENTERPRISE | 120.97 | 0 | 0 | 15
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. | SM/16622 | Augmentation | Renovation of Existing IEP (Capacity 50 Cu.M/hr) for changing of 01 No Iron Removal Filter media unit of (3.30 m dia x 1.50 M HOS) & 01 No Oxidation Chamber of (1.00 M dia x 1.00 M HOS) and painting all vessel, pipes etc. all complete for Augumentation of Ghoramara Pipe Water supply scheme, under Murshidabad Division P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000041/2024-2025 | 1941/MURD | 04/07/2024 | 03/08/2024 | KAUSHIK MAJUMDAR | 6.92 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. | SM/16622 | Augmentation | Laying of Distribution System, Repairing & Vertical Extention of Boundary Wall, Special repair and renovation of existing 1 (One) Nos Pump House and Alied Works for Augmentation work of GHORAMARA PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. (part_B) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000884/2022-2023 | 901/MURD | 29/03/2023 | 25/09/2023 | M/S RUBIET HOSSAIN | 172.57 | 2.42 | 1.41 | 11
Total | [13 empty] | 439.82 | 13.5 | 3.07