## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16624 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 1210/MURD/17 | 02/05/2023 | 02/05/2023 | Resource Division | 34.57 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16624 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under GHORA PAKHIA GANGIN ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000699/2023-2024 | 4342/MEDB | 29/12/2023 | 29/03/2024 | SREE RADHA ELECTRICAL | 21.44 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16624 | Augmentation | Prooviding FHTC Connection to 835 nos household, Laying of Rising Main, Laying of Distribution System, Overhauling of RCC 100 Cum OHR, , construction Pump House with sanitary and Water Supply Arrangement (T/W-I) , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works & Repair of Boundary Wall (140m + 50m)=190 m at T/W-I site & T/W-II site for Augmentation of Ghora Pakhia Gangin(Zone-I) Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. . | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000197/2023-2024 | 1998/MURD | 21/07/2023 | 01/01/2026 | APURBA SAHA CHOWDHURY | 179.37 | 45.51 | 25.37 | 50
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16624 | Augmentation | Continuation work order for Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Assistant Engineer (HQ), Murshidabad Division, P.H.E. Dte. For 06(Six) Months (on and from 01/05/2025 to 31/10/2025) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver, Taxes , Insurance , Fees etc. as applicable Excluding fuel, lubricant etc. as per order) Vehicle No.WB-58BV-8767 | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER ESTIMATING SECTION,Junior Engineer, Estimating Section | ORD/000013/2025-2026 | 946/MURD | 29/04/2025 | 29/10/2025 | M/S JOY MA BANAMALI | 0.9 | 0 | 0 | 20
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16624 | Augmentation | Continuation work order for Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywhere with in any trouble on daily wage basis for official used under the control of the Assistant Engineer (HQ), Murshidabad Division, P.H.E. Dte. For 06(Six) Months (on and from 01/11/2025 to 30/04/2026) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver, Taxes ,Insurance , Fees etc. as applicable Excluding fuel, lubricant etc. as per order) Vehicle No.WB-58BV-8767 | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000187/2025-2026 | 2239/MURD | 31/10/2025 | 30/04/2026 | M/S JOY MA BANAMALI | 0.89 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16624 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 09/06/2022 | RADIANT | 73.97 | 3.08 | 4.17 | 100
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16624 | Augmentation | Laying M.S pipe for interconnection Between A.I.R.P & O.H.R and Clearing chokage of Rising main at GHORAPAKIAGANGING Zone-I Water Supply Scheme under Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000825/2022-2023 | 652/MURD | 06/03/2023 | 05/04/2023 | LAXMI CONSTRUCTION | 1.86 | 1.84 | 99.12 | 100
Total | [13 empty] | 312.99 | 50.44 | 16.11