## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16752 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (Selamatipur PWSS Scheme, Block - Berhampore) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. |  | JUNIOR ENGINEER 1 | ORD/000834/2021-2022 | 3267/MURD | 05/10/2021 | 04/12/2021 | RADIANT | 3.23 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16752 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000301/2023-2024 | 1278/MURD/2 | 10/05/2023 | 10/05/2023 | Resource Division | 10.58 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16752 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 1811/MURD/02 | 20/06/2024 | 20/06/2024 | Resource Division | 16.77 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16752 | Augmentation | QUOTATION FOR SHIFTING OF PHE25KVA DTR AT SALAMATPUR REF ID. 860308681 |  |  | BILL/00651/2024-2025 |  | 16/08/2024 | 16/08/2024 | WBSEDCL | 4.47 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16752 | Augmentation | QUOTATION FOR SHIFTING OF PHE 25KVA DTR AT SALAMATPUR REF ID. 860308681 |  |  | BILL/00653/2024-2025 | 199/WBSEDCL-JJM | 22/08/2024 | 22/08/2024 | WBSEDCL | 4.47 | 0 | 0 | 0
6 | MURSHIDABAD |  | Central Drilling | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16752 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21379.28 | 0 | 0