## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. | SM/16764 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 04/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 0 | 76
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. | SM/16764 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 1043/MURD/5 | 17/04/2023 | 17/04/2023 | Resource Division | 0.69 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. | SM/16764 | Augmentation | Laying Distribution System, Rising Main, FHTC, Repairing of Boundary Wall, Pump House & Existing OHR for Augmentation of Bhalkundi Zone-III Water at Supply Scheme in Khargram Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000028/2023-2024 | 1077/MURD | 19/04/2023 | 28/02/2025 | SUJIT KUMAR SAHA | 162.99 | 0 | 0 | 30
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. | SM/16764 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-III under BHALKUNDI ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000678/2023-2024 | 3850/MEDB | 06/11/2023 | 06/02/2024 | S. K. ENTERPRISE | 22.8 | 0 | 0 | 70
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. | SM/16764 | Augmentation | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhalkundi Zone-III & adjoining mouzas Water Supply Scheme at 3rd work site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000033/2023-2024 | 1108/MURD | 24/04/2023 | 14/05/2023 | SARKAR WATER SUPPLY AGENCY | 10.67 | 0 | 0 | 100
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. | SM/16764 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 01/05/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 0 | 75
Total | [13 empty] | 361.3 | 0 | 0