## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 04/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 3.5 | 3.93 | 76
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , Zone-II under TENYA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000105/2023-2024 | 1901/MEDB | 16/06/2023 | 16/09/2023 | S. G. ENTERPRISE | 33.51 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 969 | 06/04/2023 | 06/04/2023 | Resource Division | 28.48 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1004/MURD | 11/04/2023 | 11/04/2023 | Resource Division | 28.48 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Tenya Zone - II Water Supply Scheme and Kurulia Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000109/2023-2024 | 1751/MURD | 06/07/2023 | 27/07/2023 | NADIA TUBEWELLS | 27.64 | 0 | 0 | 50
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 6.57 | 6.74 | 80
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | Augmentation | Laying Distribution System and FHTC at Bara Biadyapur Village (Village Code-315733), Tenya Village (Village-315737), Ghoshpara Village ( Village Code- 315735), Kechunia Village (Village Code-315722), Korgram Village (Village Code- 315736) & Nowapara Village (Village Code-315734) & Repairing of Over Head Reservoir (350 Cum), Pump House & Boundary wall for Augmentation of TENYA Zone-II PWSS in BHARATPUR-II Block , under Murshidabad Division,PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 5 | ORD/000041/2023-2024 | 1139/MURD | 26/04/2023 | 22/05/2026 | TANUSHREE ENTERPRISE | 172.7 | 3.31 | 1.92 | 20
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | Augmentation | Augmentation of MURADPUR JALANGI ZONE-III /Tenya Zone-II & Zone-III PWSS Laying Distribution System, of JALANGI /Bharatpur-II Block , under Murshidabad Division PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 8,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000375/2023-2024 | 2755/MURD | 01/09/2023 | 21/08/2025 | ULTRA CONSTRUCTION. | 100.45 | 0 | 0 | 95
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | Augmentation | Continuation for work order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 01.02.2025 to 31.05.2025) VEHICLE NO - WB 57E 5422 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000389/2024-2025 | 25/KSD | 24/01/2025 | 24/05/2025 | SOUMYADIP MISRA | 0.69 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | Augmentation | Continuation for work order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 28.09.2024 to 31.01.2025) VEHICLE NO - WB 57E 5422 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000371/2024-2025 | 141/KSD | 26/09/2024 | 24/01/2025 | SOUMYADIP MISRA | 0.69 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | Augmentation | Continuation for work order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 01.06.2025 to 30.09.2025) VEHICLE NO - WB 57E 5422 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000094/2025-2026 | 83/KSD | 21/05/2025 | 18/09/2025 | SOUMYADIP MISRA | 0.69 | 0 | 0 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. | SM/16765 | Augmentation | Continuation for work order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 01.10.2025 to 31.01.2026) VEHICLE NO - WB 57E 5422 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000263/2025-2026 | 121/KSD | 08/09/2025 | 06/01/2026 | SOUMYADIP MISRA | 0.69 | 0 | 0 | 0
Total | [13 empty] | 580.81 | 13.39 | 2.31