## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/16766 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-II of Mahalandi ground water based water supply scheme under Block- Kandi Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000284/2023-2024 | 3227/MEDB | 17/08/2023 | 17/11/2023 | SURAKSHA | 11.92 | 10.54 | 88.43 | 60
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/16766 | Augmentation | Construction of boundary wall at Front side of Head work site including gate of Mahalandi (Zone-II) water supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001194/2021-2022 | 336/KSD | 30/11/2021 | 14/01/2022 | A.P. CONSTRUCTION | 4.92 | 4.91 | 99.86 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/16766 | Augmentation | Construction of pathway and development of land at Head work Site of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000006/2022-2023 | 08 / KSD | 06/04/2022 | 21/05/2022 | BIMALENDU BOSE | 4.84 | 4.83 | 99.71 | 1
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/16766 | Augmentation | Supplying fitting and fixing of R.B.T Concertina fencing on wall top and construction of surface drain at Head work site of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000011/2022-2023 | 12 / KSD | 06/04/2022 | 21/05/2022 | DEBJYOTI MUKHERJEE | 4.73 | 4.71 | 99.77 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/16766 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone-II Water Supply Scheme at HW Site under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000597/2022-2023 | 3071/MURD | 17/11/2022 | 17/12/2022 | A.M. ENTERPRISE | 10.6 | 9.95 | 93.91 | 100
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/16766 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 1043/MURD/6 | 17/04/2023 | 17/04/2023 | Resource Division | 150.69 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/16766 | Augmentation | Construction of Boundary Wall & Pump House with sanitary & plumbing work (3rd & 4th T/W Site) of Mahalandi (Zone-II) Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000082/2024-2025 | 2075/MURD | 19/07/2024 | 17/09/2024 | AHAMMED ENTERPRISE | 28.77 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/16766 | Augmentation | Providing FHTC Connection to 818 nos. household , Construction of 300 Cum OHR, Laying of Distribution System, Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 200 Cum capacity of staging height 20 mtr. Repairing & Vertical Extention of Boundary Wall, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works , Construction of Pump House with sanitary and Water Supply Arrangement & Boundary Wall, for Augmentation work of MAHALANDI ZONE-II Kandi Block under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000247/2023-2024 | 2468/MURD | 09/08/2023 | 01/01/2026 | M/S. BIMALENDU BOSE | 451.48 | 141.77 | 31.4 | 10
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/16766 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well, 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone - I , Mahalandi Zone - II & Bhalkundi Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000132/2023-2024 | 1758/MURD | 06/07/2023 | 01/02/2025 | R.K. DRILLING SERVICES | 23.58 | 0 | 0 | 70
10 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. | SM/16766 | Augmentation | Construction of boundary wall at Northern side of Head work site of Mahalandi (Zone-I) water supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000110/2020-2021 | 2976/MURD | 01/12/2020 | 15/01/2021 | JYOTI TRADERS | 4.14 | 4.13 | 99.83 | 1
Total | [13 empty] | 695.67 | 180.84 | 26