## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 1180/MURD/15 | 29/04/2023 | 29/04/2023 | Resource Division | 61.77 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-III, BHANDARA ZONE - I and SURANGAPUR ZONE -I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000700/2023-2024 | 3785/MURD | 11/12/2023 | 01/01/2024 | SARKAR WATER SUPPLY AGENCY | 35.34 | 0 | 0 | 80
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 1811/MURD/07 | 20/06/2024 | 20/06/2024 | Resource Division | 34.58 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000396/2023-2024 | 711/MURD | 07/03/2024 | 07/03/2024 | Resource Division | 26 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | Augmentation | SURANGAPURPH-1 Z-I |  |  | BILL/01574/2023-2024 | 414/WBSEDCL-JJM | 06/03/2024 | 06/03/2024 | WBSEDCL | 3.67 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | Augmentation | SURANGAPUR Z-I PH-II |  |  | BILL/01572/2023-2024 | 413/WBSEDCL-JJM | 06/03/2024 | 06/03/2024 | WBSEDCL | 7.85 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | Augmentation | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000498/2024-2025 | 663/MURD | 19/03/2025 | 23/05/2025 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. UNDER MEDB, PHE, DTE. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000529/2024-2025 | 315/MEDB | 10/02/2025 | 27/10/2025 | M/S S. S. ENTERPRISE (DOMKAL) | 37.13 | 0 | 0 | 40
9 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | Augmentation | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490 another 160 days from 12/01/2025 to 20/06/2025. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000249/2024-2025 | 06/BSD | 08/01/2025 | 17/06/2025 | ABIDA CONSTRUCTION | 0.93 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | Augmentation | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490,91days from 01/09/2025 to 30/11/2025. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000155/2025-2026 | 125/BSD | 01/09/2025 | 01/12/2025 | ABIDA CONSTRUCTION | 0.53 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | Augmentation | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490 another 91days from 21/06/2025 to 19/09/2025. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000101/2025-2026 | 122/BSD | 20/06/2025 | 19/09/2025 | ABIDA CONSTRUCTION | 0.53 | 0 | 0 | 0
12 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/16767 | Augmentation | Augmentation of SURANGAPUR Zone-I (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000003/2023-2024 | 952/MURD | 05/04/2023 | 01/03/2025 | M/S NIRAPADA BHATTACHARJEE | 329.64 | 0 | 0 | 100
Total | [13 empty] | 596.83 | 0 | 0