## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16770 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV ,Zone-II under AMINABAD ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000077/2023-2024 | 3763/MEDB | 03/11/2023 | 03/02/2024 | B. T. PROJECTS PVT. LTD. | 45.69 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16770 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 1210/MURD/15 | 02/05/2023 | 02/05/2023 | Resource Division | 37.48 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16770 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 24/09/2023 | MERCHANDISE-INDIA | 26.8 | 4.47 | 16.67 | 100
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16770 | Augmentation | NEW CONNECTION AT AMINABAD Z-II PH-II |  |  | BILL/00176/2024-2025 | 16/WBSEDCL-JJM | 16/04/2024 | 16/04/2024 | WBSEDCL | 6.25 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16770 | Augmentation | NEW CONNECTION AT AMINABAD Z-II PH-I |  |  | BILL/00175/2024-2025 | 15/WBSEDCL-JJM | 16/04/2024 | 16/04/2024 | WBSEDCL | 13.07 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16770 | Augmentation | Formal work order for Augmentation of Aminabad Zone-II Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000846/2022-2023 | 773/MURD | 17/03/2023 | 14/08/2025 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 726.14 | 161.01 | 22.17 | 35
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16770 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Aminabad (Zone-II) & Katakobra Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 5 | ORD/000121/2023-2024 | 1762/MURD | 06/07/2023 | 27/07/2023 | R.K. DRILLING SERVICES | 35.37 | 10.11 | 28.6 | 66
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/16770 | Augmentation | Supply of different types C.I Specials at Islampur Sub-Divisional Store for different water supply schemes under Islampur sub-Division, under Murshidabad Division, P.H.E. Dte in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000132/2024-2025 | 2674/MURD | 25/09/2024 | 25/05/2025 | MAKALI ENGINEERING CORPORATION | 32.46 | 8.09 | 24.92 | 100
Total | [13 empty] | 923.26 | 183.68 | 19.89