## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | BABARPUR AND ADJOINING MOUJAS PWSS | SM/16814 | New | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 1075/MURD/17 | 19/04/2023 |  | Resource Division | 1.09 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Central Drilling | BABARPUR AND ADJOINING MOUJAS PWSS | SM/16814 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). |  |  | ORD/000209/2023-2024 | 2203/CDD | 01/03/2024 | 29/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | BABARPUR AND ADJOINING MOUJAS PWSS | SM/16814 | New | NEW CONNECTION AT BABARPUR PH-I |  |  | BILL/01592/2023-2024 | 430/WBSEDCL-JJM | 12/03/2024 |  | WBSEDCL | 4.31 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | BABARPUR AND ADJOINING MOUJAS PWSS | SM/16814 | New | NEW CONNECTION AT BABARPUR PH-I |  |  | BILL/01592/2023-2024 | 430/WBSEDCL-JJM | 12/03/2024 |  | WBSEDCL | 4.31 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Murshidabad Division | BABARPUR AND ADJOINING MOUJAS PWSS | SM/16814 | New | BABARPUR PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000151/2023-2024 | 1899/MURD | 17/07/2023 | 14/11/2023 | DIPAYAN DEY | 157.25 | 42.59 | 27.08 | 40
Total | [13 empty] | 278.01 | 42.59 | 15.32