## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti-II | Berhampore Mechanical | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . | SM/16815 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hazipur Part-A village, Block:- Suti-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000196/2023-2024 | 3055/MEDB | 02/08/2023 | 02/11/2023 | M/S MANABESH ROY | 6.15 | 0 | 0 | 0
2 | MURSHIDABAD | Suti-II | Murshidabad Division | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . | SM/16815 | New | Material Requisition To Resource Division |  |  | RTOR000228/2023-2024 | 1219/MURD/12 | 03/05/2023 | 03/05/2023 | Resource Division | 14.34 | 0 | 0 | 0
3 | MURSHIDABAD | Suti-II | Murshidabad Division | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . | SM/16815 | New | Ground Water based piped water supply scheme for Hazipur Part- B village, Block:- Suti-II, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000214/2023-2024 | 2329/MURD | 02/08/2023 | 01/10/2023 | SHIRSHENDU MUKHERJEE | 30.55 | 0 | 0 | 0
4 | MURSHIDABAD | Suti-II | Berhampore Mechanical | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . | SM/16815 | New | NEW CONNECTION AT HAZIPUR MINI PH-I |  |  | BILL/00518/2024-2025 |  | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.13 | 0 | 0 | 0
5 | MURSHIDABAD | Suti-II | Berhampore Mechanical | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . | SM/16815 | New | NEW CONNECTION AT HAZIPUR MINI PH-II |  |  | BILL/01095/2024-2025 |  | 12/11/2024 | 12/11/2024 | WBSEDCL | 0.59 | 0 | 0 | 0
6 | MURSHIDABAD | Suti-II | Berhampore Mechanical | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . | SM/16815 | New | NEW CONNECTION AT HAZIPUR MINI PH-I |  |  | BILL/00524/2024-2025 | 164/WBSEDCL-JJM | 29/07/2024 | 29/07/2024 | WBSEDCL | 0.13 | 0 | 0 | 0
7 | MURSHIDABAD | Suti-II | Berhampore Mechanical | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . | SM/16815 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hazipur Part-B village, Block:- Suti-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000197/2023-2024 | 3056/MEDB | 02/08/2023 | 02/10/2025 | MONI ELECTRICAL WORKS | 6.27 | 0 | 0 | 20
8 | MURSHIDABAD | Suti-II | Murshidabad Division | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . | SM/16815 | New | Ground Water based piped water supply scheme for Hazipur Part- A village, Block:- Suti-II, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000259/2023-2024 | 2495/MURD | 11/08/2023 | 02/01/2025 | MUKTI ENTERPRISE | 30.47 | 0 | 0 | 100
Total | [13 empty] | 88.63 | 0 | 0