## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Berhampore Mechanical | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS | SM/16816 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Jagannathpur ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000250/2023-2024 | 3685/MEDB | 03/11/2023 | 03/02/2024 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 22.23 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Murshidabad Division | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS | SM/16816 | New | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 1075/MURD/19 | 19/04/2023 | 19/04/2023 | Resource Division | 1.38 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS | SM/16816 | New | NEW SERVICE CONNECTION AT JAGANNATHPUR PH II, ID304233698 |  |  | BILL/01209/2023-2024 | 262/WBSEDCL-JJM | 24/01/2024 | 24/01/2024 | WBSEDCL | 5.04 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS | SM/16816 | New | NEW SERVICE CONNECTION AT JAGANNATHPUR PH I, ID304233735 |  |  | BILL/01208/2023-2024 | 261/WBSEDCL-JJM | 24/01/2024 | 24/01/2024 | WBSEDCL | 6.64 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Murshidabad Division | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS | SM/16816 | New | JAGANNATHPUR PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000659/2023-2024 | 3528/MURD | 10/11/2023 | 31/03/2025 | SOUMYADIP MISRA | 367.89 | 0 | 0 | 25
Total | [13 empty] | 403.17 | 0 | 0